SADRS Implementation Plan Smart ATM Defense & Response System ¦ Claude Sonnet 4.6 — Full Dev Roadmap ¦ Claude Sonnet 4.6

Implementation Overview

This document is the complete sprint-level implementation plan for building SADRS from scratch. It covers 5 phases across 15 months, broken into concrete engineering tasks with owners, durations, and deliverables. The stack is Python (Pi firmware) + Flask (backend) + Next.js (dashboard) + Claude Sonnet 4.6 (AI) + Arduino C (sensor firmware).

| Phase | Duration | Focus | Key Output |
| --- | --- | --- | --- |
| Phase 1 | Months 1–3 | Hardware Core | Panic PIN + Sensors + GSM Alert |
| Phase 2 | Months 4–7 | ML + AI Layer | CCTV Pipeline + Claude Integration |
| Phase 3 | Months 8–9 | Integration & Security | Full System E2E + Security Audit |
| Phase 4 | Months 10–15 | Pilot Deployment | 50–100 Live ATMs + Real Data |
| Phase 5 | Month 16+ | Scale & Innovate | Blockchain + Federated Learning |

PHASE 1: HARDWARE CORE & ALERT PIPELINE Months 1–3 (12 Weeks) ¦ MVP Foundation

Sprint 1–2: Environment Setup (Weeks 1–4)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T1.1 | Flash Raspberry Pi OS Lite (64-bit) + configure headless SSH + static IP | Embedded Eng | 2 days | Core |
| T1.2 | Set up Python 3.11 virtual env + install PySerial, RPi.GPIO, Flask, cryptography libs | Embedded Eng | 1 day | Core |
| T1.3 | Flash Arduino Nano with sensor polling firmware (C++); validate serial comms with Pi | Embedded Eng | 3 days | Core |
| T1.4 | Wire MEMS vibration sensor (SW-420) to Arduino A0; validate ADC readings in Python | Embedded Eng | 2 days | Core |
| T1.5 | Wire MPU-6050 (I2C) to Arduino; validate tilt X/Y readings; set calibration baseline | Embedded Eng | 2 days | Core |
| T1.6 | Wire PIR HC-SR501 to Arduino D2; validate motion detection event via serial | Embedded Eng | 1 day | Core |
| T1.7 | Wire DHT22 temperature sensor; validate readings within ±0.5°C | Embedded Eng | 1 day | Core |
| T1.8 | Set up PostgreSQL DB locally + create schema (atm_units, incidents, sensor_logs) | Backend Eng | 2 days | Core |
| T1.9 | Create GitHub repo + CI pipeline (pytest + linting on PR) | DevOps | 1 day | Core |

Sprint 3–4: Panic PIN System (Weeks 5–8)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T2.1 | Implement PIN input capture via ATM keypad GPIO simulation (test with USB numpad) | Embedded Eng | 2 days | MVP |
| T2.2 | Build panic PIN hash verification module: SHA-256 + bcrypt salt comparison in Python | Backend Eng | 2 days | MVP |
| T2.3 | Implement decoy response logic: display 'Processing...' on terminal output while alert fires | Embedded Eng | 1 day | MVP |
| T2.4 | Wire 4-channel relay module to Pi GPIO; test relay switching under Python control | Embedded Eng | 1 day | MVP |
| T2.5 | Wire servo motor / solenoid lock to relay channel 1; validate lock/unlock on GPIO signal | Embedded Eng | 2 days | MVP |
| T2.6 | Wire SIM800C GSM module to Pi UART; validate AT commands (AT, AT+CMGS) in Python | Embedded Eng | 3 days | MVP |
| T2.7 | Implement gsm_alert.py: send encrypted SMS with ATM ID + GPS stub to test number | Embedded Eng | 2 days | MVP |
| T2.8 | Implement GPS coordinate fetching (static config for fixed ATMs; GPSd for mobile) | Embedded Eng | 1 day | MVP |
| T2.9 | Full Panic PIN E2E test: keypad → hash check → relay lock → GSM SMS → < 30 seconds | QA | 2 days | MVP |

Sprint 5–6: Sensor Pipeline + Backend API v1 (Weeks 9–12)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T3.1 | Build sensor_monitor.py: threaded loop reading vibration/tilt/PIR/temp from Arduino | Embedded Eng | 3 days | Core |
| T3.2 | Implement threshold engine: configurable per-sensor alert thresholds with dual-sensor corroboration | Embedded Eng | 2 days | Core |
| T3.3 | Build Flask API skeleton: /heartbeat, /incidents (POST), /config/:atm_id (GET) | Backend Eng | 3 days | Core |
| T3.4 | Implement HMAC-signed API key auth for Pi → Backend calls | Backend Eng | 2 days | Core |
| T3.5 | Implement incident creation flow: Pi detects → POST to backend → backend stores in DB | Backend Eng | 2 days | Core |
| T3.6 | Implement Pi heartbeat sender (every 60s) + backend offline detection (3 missed = alert) | Embedded Eng | 2 days | Core |
| T3.7 | Set up systemd service on Pi: SADRS auto-starts on boot, auto-restarts on crash | DevOps | 1 day | Core |
| T3.8 | Phase 1 integration test: all sensors + panic PIN + GSM + backend reporting together | QA | 3 days | Core |
| T3.9 | Phase 1 review: benchmark alert latency across 50 trials; document results | All | 1 day | Core |

Phase 1 Exit Criteria

- Panic PIN GSM alert delivered < 30 seconds in ≥ 95% of 50 test runs

- All 4 sensors read correctly; threshold breach triggers incident in DB

- Pi heartbeat confirmed on backend; offline detection working

- Relay/lock actuates reliably across 100 cycles

PHASE 2: ML + AI LAYER (CCTV + CLAUDE) Months 4–7 (16 Weeks) ¦ AI-Powered Detection

Sprint 7–8: ML Model Development (Weeks 13–16)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T4.1 | Assemble ATM CCTV dataset: 2,000+ labeled frames across 6 threat classes (loitering, weapon, crowd, mask, aggressive, normal) | ML Eng | 1 week | AI |
| T4.2 | Data augmentation pipeline: brightness variation, blur, occlusion, time-of-day simulation | ML Eng | 3 days | AI |
| T4.3 | Train YOLOv8-nano on labeled dataset using Google Colab GPU; target mAP ≥ 75% | ML Eng | 1 week | AI |
| T4.4 | Evaluate model on held-out test set; measure false positive rate per class; iterate | ML Eng | 3 days | AI |
| T4.5 | Convert best checkpoint to TensorFlow Lite (FP16 quantized) using tflite_convert | ML Eng | 2 days | AI |
| T4.6 | Benchmark TFLite model on Pi 4: measure FPS at 640×480; target ≥ 10 FPS | ML Eng | 2 days | AI |
| T4.7 | Build model versioning system: backend tracks model_version per ATM for OTA rollout | Backend Eng | 2 days | AI |
| T4.8 | Set up MLflow or W&B experiment tracking for future model iterations | ML Eng | 1 day | AI |

Sprint 9–10: CCTV Pipeline on Pi (Weeks 17–20)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T5.1 | Integrate IP camera: OpenCV VideoCapture with RTSP or USB; validate 15+ FPS capture on Pi | Embedded Eng | 2 days | AI |
| T5.2 | Build cctv_inference.py: threaded inference loop using TFLite Interpreter | ML Eng | 3 days | AI |
| T5.3 | Implement 3-frame confirmation logic: maintain frame history; trigger only on 3 consecutive threat frames | ML Eng | 2 days | AI |
| T5.4 | Implement corroboration check: CCTV threat must be confirmed by PIR OR vibration signal | Embedded Eng | 2 days | AI |
| T5.5 | Build 30-second pre-alert ring buffer: retain recent frames in RAM for clip extraction | ML Eng | 2 days | AI |
| T5.6 | Implement clip_extractor.py: extract 30s + 10s post-alert clip; encode to MP4; AES-256 encrypt | ML Eng | 2 days | AI |
| T5.7 | Implement S3 uploader: boto3-based async upload of encrypted clip; retry on failure | Backend Eng | 2 days | AI |
| T5.8 | Add time-context weighting: flag confidence boosted between 11PM–5AM | ML Eng | 1 day | AI |
| T5.9 | Full CCTV pipeline test: simulate threat → confirm frames → extract clip → upload S3 | QA | 2 days | AI |

Sprint 11–12: Claude Sonnet 4.6 Integration (Weeks 21–24)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T6.1 | Set up Anthropic SDK (anthropic Python lib); configure API key in backend env | Backend Eng | 1 day | AI |
| T6.2 | Build claude_analyst.py service: formats incident data → calls Claude Sonnet 4.6 → returns summary | Backend Eng | 3 days | AI |
| T6.3 | Design and test incident summary system prompt; evaluate 50 synthetic incidents for quality | ML Eng | 2 days | AI |
| T6.4 | Build false-positive reasoning endpoint: Claude evaluates ambiguous ML detections; returns confirm/dismiss | Backend Eng | 3 days | AI |
| T6.5 | Build SMS alert text generator: Claude compresses incident to ≤ 160 chars for GSM dispatch | Backend Eng | 2 days | AI |
| T6.6 | Implement fallback: if Claude API call fails/times out (>10s), use template-based summary | Backend Eng | 1 day | AI |
| T6.7 | Add Claude response caching: same incident type + ATM zone → return cached summary if <5min old | Backend Eng | 2 days | AI |
| T6.8 | Cost monitoring: add per-call token logging to DB; build admin endpoint to view Claude API spend | Backend Eng | 1 day | AI |
| T6.9 | Integration test: CCTV threat detected → clip uploaded → Claude summary generated → visible on dashboard | QA | 2 days | AI |

Sprint 13–14: Bank Security Dashboard (Weeks 25–28)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T7.1 | Scaffold Next.js 14 project with Tailwind CSS; set up ESLint + Prettier + Husky | Frontend Eng | 1 day | MVP |
| T7.2 | Build authentication: JWT login page + protected route wrapper + token refresh | Frontend Eng | 2 days | MVP |
| T7.3 | Build dashboard home: ATM map (Leaflet.js) with status dots (green/amber/red) | Frontend Eng | 4 days | MVP |
| T7.4 | Build incident feed: real-time card list via Socket.IO; shows trigger type, ATM, time, severity | Frontend Eng | 3 days | MVP |
| T7.5 | Build incident detail view: Claude summary, sensor readings, CCTV clip player, GPS map, action buttons | Frontend Eng | 4 days | MVP |
| T7.6 | Build ATM health monitor: per-unit uptime, sensor health bars, firmware version, last heartbeat | Frontend Eng | 2 days | MVP |
| T7.7 | Build alert config panel: manage police numbers, thresholds, panic PIN admin | Frontend Eng | 2 days | MVP |
| T7.8 | Build incident log / audit trail: filterable table with export to CSV | Frontend Eng | 2 days | MVP |
| T7.9 | API integration: connect all dashboard views to Flask REST API + Socket.IO events | Frontend Eng | 3 days | MVP |
| T7.10 | Cross-browser test (Chrome, Firefox, Edge); mobile responsive validation | QA | 2 days | MVP |

Phase 2 Exit Criteria

- ML model FP rate < 5% on 1,000 held-out frames

- CCTV pipeline: threat → confirmed → clip uploaded in < 60 seconds

- Claude summary appears on dashboard within 90 seconds of incident

- Dashboard renders all incident data correctly; operator actions (confirm/dismiss) persist to DB

PHASE 3: INTEGRATION, SECURITY & HARDENING Months 8–9 (8 Weeks) ¦ Production Readiness

Sprint 15–16: End-to-End Integration Testing (Weeks 29–32)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T8.1 | Build SADRS lab test rig: mock ATM with all hardware, simulated attack scenarios | QA | 3 days | Core |
| T8.2 | Run 100 Panic PIN E2E tests; measure and log latency for each; target 100% < 30s | QA | 3 days | Core |
| T8.3 | Run 50 CCTV threat scenarios; validate corroboration logic; measure false positive rate | QA | 3 days | Core |
| T8.4 | Simulate GSM network failure: verify Wi-Fi fallback alert dispatched successfully | QA | 2 days | Core |
| T8.5 | Simulate Wi-Fi failure: verify GSM primary path unaffected; evidence upload queued | QA | 2 days | Core |
| T8.6 | Simulate Pi crash mid-incident: verify systemd restart < 90 seconds; heartbeat resumes | QA | 2 days | Core |
| T8.7 | Test OTA firmware update: push update from backend; validate Pi applies and reboots correctly | DevOps | 2 days | Core |
| T8.8 | Load test: simulate 100 simultaneous ATM incidents; verify backend handles without queue backup | Backend Eng | 2 days | Core |

Sprint 17–18: Security Audit & Compliance (Weeks 33–36)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T9.1 | Penetration test: attempt API access without valid API key / JWT; verify 401 on all protected endpoints | Security | 3 days | Core |
| T9.2 | Verify AES-256 encryption on all S3 clips; validate encrypted payload cannot be decoded without key | Security | 2 days | Core |
| T9.3 | Verify panic PIN hash: confirm plaintext PIN is never logged anywhere in system (grep logs + DB) | Security | 1 day | Core |
| T9.4 | Test tamper enclosure: trigger tamper switch; verify alert fires before Pi shuts down | Hardware Eng | 1 day | Core |
| T9.5 | RBAC validation: confirm bank admin, operator, auditor roles enforce correct permissions on all routes | Backend Eng | 2 days | Core |
| T9.6 | Data retention test: verify 72-hour auto-delete of raw video; 90-day incident log retention | Backend Eng | 1 day | Core |
| T9.7 | DPDPA compliance review: document data flows; confirm no PII transmitted without encryption | Legal/Product | 3 days | Core |
| T9.8 | Prepare RBI security compliance checklist mapping SADRS features to guidelines | Product | 2 days | Core |
| T9.9 | Document all findings; fix critical and high severity issues; re-test | Security | 3 days | Core |

Phase 3 Exit Criteria

- Zero critical/high security vulnerabilities open

- All 12 Technical Success Criteria from TRD passed

- Full documentation: API docs, hardware setup guide, operator training manual complete

- Stakeholder demo completed with bank and police representatives

PHASE 4: PILOT DEPLOYMENT Months 10–15 (24 Weeks) ¦ Live ATMs — Real World

Pilot Setup (Weeks 37–40)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T10.1 | Partner with 2 public sector banks (SBI / PNB); sign MoU; identify 50 pilot ATM locations | Business Dev | 2 weeks | MVP |
| T10.2 | Onboard police stations in pilot zones: register numbers, test alert receipt, brief officers | Operations | 1 week | MVP |
| T10.3 | Production hardware build: assemble 50 SADRS kits; QA each unit in lab before shipping | Hardware Eng | 2 weeks | MVP |
| T10.4 | On-site installation: deploy and configure each ATM unit; run post-install drill at each site | Field Eng | 3 weeks | MVP |
| T10.5 | Bank operator training: 2-day training program on dashboard, alert response, incident management | Operations | 1 week | MVP |

Live Operations & Monitoring (Weeks 41–60)

| Task ID | Task | Owner | Duration | Status |
| --- | --- | --- | --- | --- |
| T11.1 | 24/7 system monitoring: uptime alerts via PagerDuty for any ATM offline > 5 minutes | DevOps | Ongoing | Core |
| T11.2 | Weekly false positive review: bank security team reviews all ML-flagged incidents; labels fed back for model retraining | ML Eng | Weekly | AI |
| T11.3 | Monthly model fine-tuning: retrain on accumulated labeled pilot data; push updated TFLite via OTA | ML Eng | Monthly | AI |
| T11.4 | Incident response tracking: log all actual crime incidents; correlate with SADRS alert data | Product | Ongoing | Core |
| T11.5 | Bank operator feedback sessions: bi-weekly 30-min calls to collect UX feedback on dashboard | Product | Bi-weekly | Core |
| T11.6 | Police liaison review: monthly meeting with police to assess alert quality and response times | Operations | Monthly | Core |
| T11.7 | Performance report: monthly report on uptime, alert latency, FP rate, crime incident correlation | Product | Monthly | Core |
| T11.8 | Phase 4 final report: compile 6-month pilot results; prepare case study for Phase 5 scale | Product | Week 60 | Core |

Phase 4 Exit Criteria

- ≥ 50 ATMs live and operational for ≥ 30 continuous days

- Police alert delivery success rate ≥ 95% in live environment

- System uptime ≥ 99.5% across all pilot ATMs over 90 days

- Bank security team satisfaction ≥ 4/5 in post-pilot survey

- ML FP rate in live environment < 8% (slightly relaxed from lab due to real-world variance)

PHASE 5: SCALE, INNOVATION & COMMERCIALIZATION Month 16+ (Ongoing) ¦ Future Roadmap

Blockchain Audit Trail

- Hash each incident record (sensor data + alert payload + Claude summary) to Ethereum/Hyperledger

- Provides tamper-proof evidence chain admissible in court proceedings

- Smart contract auto-releases incident hash to police on confirmed alert

- Implementation: web3.py + private Hyperledger Fabric network with bank + police nodes

Biometric Stress Detection

- Integrate thermal camera module to detect physiological stress markers (elevated skin temp, rapid movement)

- Train secondary classifier on thermal + RGB combined features

- Adds a fourth detection pipeline complementing Panic PIN for involuntary stress signaling

Federated Learning

- Share anonymized model gradient updates across all SADRS-equipped ATMs without sharing raw video

- Central model server aggregates updates using FedAvg; pushes improved global model via OTA

- Implementation: PySyft or Flower federated learning framework

Commercial Licensing

- SaaS model: ₹2,000–5,000 per ATM per month (monitoring + model updates + cloud + support)

- Insurance partnership: Negotiate reduced ATM insurance premiums for SADRS-equipped banks

- International expansion: Southeast Asia and Africa markets with similar ATM security gaps

- ATM manufacturer licensing: OEM integration deals with NCR, Diebold Nixdorf

Team & Skills Required

| Role | Responsibilities | Key Skills |
| --- | --- | --- |
| Embedded Engineer (2) | Pi firmware, Arduino sensor code, hardware wiring, GSM integration | Python, C++, RPi.GPIO, PySerial, Electronics |
| ML Engineer (1) | Model training, TFLite conversion, CCTV pipeline, federated learning | TensorFlow, PyTorch, OpenCV, YOLOv8, Python |
| Backend Engineer (2) | Flask API, PostgreSQL, Claude integration, S3, Auth, WebSocket | Python, Flask, PostgreSQL, AWS, Anthropic SDK |
| Frontend Engineer (1) | Next.js dashboard, Socket.IO, Leaflet maps, responsive design | React, Next.js, Tailwind, TypeScript |
| DevOps Engineer (1) | CI/CD, Docker, AWS EC2/RDS/S3, Pi OTA, monitoring | Docker, AWS, GitHub Actions, systemd |
| Security Engineer (0.5) | Pen testing, encryption review, DPDPA compliance, audit logging | Network security, AES/JWT/TLS, compliance |
| Product / QA (1) | PRD/TRD ownership, test plans, bank/police liaison, pilot ops | Product management, test automation, stakeholder mgmt |

Implementation Risk Radar

| Risk | Phase | Severity | Mitigation |
| --- | --- | --- | --- |
| Pi 4 insufficient for real-time TFLite + 3 threads | 2 | HIGH | Benchmark early (T4.6); fallback: Pi 5 or Google Coral USB TPU |
| GSM AT command timing issues with SIM800C | 1 | MEDIUM | Use proven PySerial + AT command library; extensive T2.6 testing |
| ATM keypad GPIO integration varies by ATM model | 1 | HIGH | Use USB HID keypad as overlay; avoids ATM firmware dependency |
| Claude API latency spike > 10s | 2 | MEDIUM | 10s timeout + template fallback (T6.6); cache similar summaries (T6.7) |
| Bank IT reluctant to allow hardware install | 4 | HIGH | Retrofit kit touches no ATM internals; needs only power + Ethernet |
| False positives cause police alert fatigue | 4 | HIGH | Strict 3-frame + corroboration rule; human confirm before police auto-call |
| Pilot ATM vandalism / theft of Pi unit | 4 | MEDIUM | Tamper-evident steel enclosure; tamper alert on any enclosure open |

SADRS Implementation Plan  |  Claude Sonnet 4.6 Powered  |  Smart India Hackathon 2024